## Sheet1
WBS Code | Deliverable / Task
1 | Backend Core & Authentication
1.1 | Database Models
1.1.1 | User model
1.1.2 | Document model
1.1.3 | Chunk model (pgvector)
1.1.4 | Tender model
1.1.5 | Search history model
1.2 | Authentication & Authorization
1.2.1 | Register endpoint
1.2.2 | Login endpoint + JWT issuance
1.2.3 | Password hashing (bcrypt)
1.2.4 | Role-based access control middleware
1.2.5 | Account lockout after failed attempts
1.2.6 | Admin user management endpoints
1.2.7 | Current user profile endpoint
1.3 | Shared File Management
1.3.1 | Upload handler (size/type validation)
1.3.2 | Structured storage directory layout
1.3.3 | Unique file naming
1.3.4 | Secure authenticated download endpoint
1.3.5 | In-browser PDF preview
2 | Case Study Module
2.1 | Ingestion Pipeline
2.1.1 | Multi-format upload (PDF/DOCX/PPTX/PNG/JPG)
2.1.2 | PDF text extraction (PyMuPDF)
2.1.3 | DOCX text extraction (python-docx)
2.1.4 | PPTX text extraction (python-pptx)
2.1.5 | Embedded image extraction
2.1.6 | OCR fallback for scanned pages (Tesseract)
2.1.7 | Text chunking (800 tok / 100 overlap)
2.1.8 | Embedding generation (text-embedding-004)
2.1.9 | Store embeddings in pgvector
2.1.10 | Store metadata in PostgreSQL
2.1.11 | Background ingestion via Celery task
2.1.12 | Bulk folder upload
2.2 | Search & Retrieval
2.2.1 | Free-text query endpoint (20-5000 chars)
2.2.2 | Query embedding + similarity search
2.2.3 | Result formatting (score, tags, summary)
2.2.4 | Download links per result
2.2.5 | Thumbnail image previews
2.2.6 | LLM relevance explanation (Gemini Flash)
2.2.7 | Search history logging
2.2.8 | Search form / text area component
2.2.9 | Result card component
2.2.10 | Expandable detail view
3 | Tender Module
3.1 | Upload & Parsing
3.1.1 | PDF/DOCX upload endpoint
3.1.2 | Per-page text extraction with page tracking
3.1.3 | Table extraction to structured text
3.1.4 | OCR fallback for scanned pages
3.1.5 | Page-aware chunking (2000 tok / 200 overlap)
3.2 | Requirement Extraction
3.2.1 | LLM extraction prompt + JSON schema
3.2.2 | Retry logic for failed chunks
3.2.3 | Full-document coverage guarantee
3.2.4 | Merge & deduplicate requirements
3.3 | Document Matching
3.3.1 | Company document catalog + tagging
3.3.2 | Semantic + keyword matching engine
3.3.3 | Confidence scoring
3.3.4 | Review UI: accept/reject/reassign
3.4 | Report Generation
3.4.1 | DOCX report builder (python-docx)
3.4.2 | PDF export of report
3.5 | Folder Assembly
3.5.1 | Folder creation ({TenderName}_{Date})
3.5.2 | Required Documents subfolder organization
3.5.3 | ZIP packaging for download
3.6 | Progress Tracking
3.6.1 | WebSocket progress channel
3.6.2 | 8-step Celery pipeline orchestration
3.6.2 | Resume/reconnect handling
3.7 | Tender Frontend
3.7.1 | Drag-and-drop upload zone
3.7.2 | Live progress bar with step labels
3.7.3 | Requirements table view
3.7.4 | Review panel + Finalize button
4 | Methodology Module
4.1 | Ingestion & Indexing
4.1.1 | PDF/DOCX upload
4.1.2 | Full-text index (tsvector) + embeddings
4.2 | Search & Browse
4.2.1 | Name/topic search endpoint
4.2.2 | Performance tuning (<=2s response)
4.2.3 | Result formatting (title, type, score, date)
4.2.4 | Download from results
4.2.5 | In-browser PDF preview
4.2.6 | Paginated browse-all list
4.3 | Methodology Frontend
4.3.1 | Search bar with instant results
4.3.2 | Document grid/list with file-type icons
5 | Dashboard
5.1 | Three clickable module cards
5.2 | Recent Activity feed
5.3 | Summary statistics
5.4 | Dashboard stats endpoint
6 | Frontend Shell & Shared UI
6.1 | Root layout + fonts
6.2 | Navbar component
6.3 | Sidebar component
6.4 | Login page
6.5 | Auth hook + API client
6.6 | WebSocket connection manager
7 | Integration & Testing
7.1 | Backend Testing
7.1.1 | Unit tests: auth & RBAC
7.1.2 | Unit tests: chunking & embeddings
7.1.3 | Unit tests: tender pipeline steps
7.1.4 | Integration tests: end-to-end search flows
7.2 | Frontend Testing
7.2.1 | Component testing (forms, cards, tables)
7.2.2 | WebSocket progress UI testing
7.3 | System Testing
7.3.1 | Load/performance testing
7.3.2 | Cross-browser testing
7.3.3 | Security testing
7.3.4 | User Acceptance Testing (UAT)
8 | Deployment & Documentation
8.1 | Production Docker Compose deployment
8.2 | Database migration to production
8.3 | User documentation / manual
8.4 | Technical / handover documentation
8.5 | Final demo & presentation