## WBS
WBS Code | Deliverable / Task | Level | Linked Requirement ID(s) | Description | Owner | Start Date | End Date | Est. Effort (days) | Status | Dependencies | Notes
1 | Backend Core & Authentication | 1 | [6 empty] | Not Started
1.1 | Database Models | 2 | [6 empty] | Not Started
1.1.1 | User model | 3 | AUTH-01..06 | SQLAlchemy model + Alembic migration, includes role field for RBAC |  |  |  |  | Not Started
1.1.2 | Document model | 3 | LIB-IDX-01..04 | Shared metadata model for Case Studies / Methodology / Company Documents |  |  |  |  | Not Started
1.1.3 | Chunk model (pgvector) | 3 | LIB-IDX-05 | Embedding storage schema for evidence library |  |  |  |  | Not Started
1.1.4 | Tender model | 3 | TN-ING-01 | Tender + extracted requirement schema |  |  |  |  | Not Started
1.1.5 | Requirement row model | 3 | TN-EXT-02 | Page/Section/Clause/Marks/Evidence fields, one row per extracted requirement |  |  |  |  | Not Started
1.1.6 | Audit log model | 3 | AUTH-04 | Admin audit trail of user actions and tender runs |  |  |  |  | Not Started
1.2 | Authentication & Authorization | 2 | [6 empty] | Not Started
1.2.1 | Register endpoint | 3 | AUTH-01 | POST /api/auth/register - name, email, password |  |  |  |  | Not Started
1.2.2 | Login endpoint + JWT issuance | 3 | AUTH-02 | POST /api/auth/login, issues JWT access token |  |  |  |  | Not Started
1.2.3 | Token refresh endpoint | 3 | AUTH-03 | 24h expiry + refresh endpoint |  |  |  |  | Not Started
1.2.4 | Role-based access control middleware | 3 | AUTH-04 | Admin / User enforcement across all API endpoints |  |  |  |  | Not Started
1.2.5 | Password hashing (bcrypt) | 3 | AUTH-05 | Encrypt passwords prior to storage in PostgreSQL |  |  |  |  | Not Started
1.2.6 | Account lockout after failed attempts | 3 | AUTH-06 | 15 min lock after 5 consecutive failed logins |  |  |  |  | Not Started
2 | Tender Ingestion Module (Stage 1) | 1 | [6 empty] | Not Started
2.1 | Upload Handling | 2 | [6 empty] | Not Started
2.1.1 | Tender/RFP PDF upload endpoint | 3 | TN-ING-01 | Accept uploads up to 500+ pages and 100 MB |  |  |  |  | Not Started
2.1.2 | Page-accurate text & table extraction | 3 | TN-ING-02 | Preserve exact page numbers during extraction |  |  |  |  | Not Started
2.1.3 | OCR fallback for scanned pages | 3 | TN-ING-06 | Tesseract OCR applied prior to chunking |  |  |  |  | Not Started
2.2 | Section-Aware Chunking | 2 | [6 empty] | Not Started
2.2.1 | Section boundary detection | 3 | TN-ING-03 | Detect SPN, Instructions to Proposers, PDS, Evaluation Criteria, Section VII, Annexes |  |  |  |  | Not Started
2.2.2 | Sequential page-bounded chunking | 3 | TN-ING-04 | ~2000 token chunks, page 1 to final page |  |  |  |  | Not Started
2.2.3 | Sliding page overlap | 3 | TN-ING-04 | ~200 token overlap so cross-page requirements are preserved |  |  |  |  | Not Started
2.2.4 | Guard against single-pass whole-document ingestion | 3 | TN-ING-05 | Prevents requirement truncation/compression |  |  |  |  | Not Started
3 | Requirement & Scoring Extraction Module (Stage 2) | 1 | [6 empty] | Not Started
3.1 | LLM Extraction Pipeline | 2 | [6 empty] | Not Started
3.1.1 | Chunk extraction prompt + strict JSON schema | 3 | TN-EXT-01 | Sequential per-chunk LLM extraction |  |  |  |  | Not Started
3.1.2 | Field extraction | 3 | TN-EXT-02 | Page No., Section, Clause/Ref, Description, Mandatory/Advisory flag, Impact Type, Marks, Evidence Required |  |  |  |  | Not Started
3.1.3 | Retry logic + manual-review flagging | 3 | TN-EXT-06 | Up to 3 retries, then flag chunk as Needs Manual Review |  |  |  |  | Not Started
3.2 | Master Table Assembly | 2 | [6 empty] | Not Started
3.2.1 | Append chunk outputs to running master table | 3 | TN-EXT-03 | Unified document-ordered table |  |  |  |  | Not Started
3.2.2 | Merge & deduplicate overlapping requirements | 3 | TN-EXT-04 | De-dupe results from overlapping page boundaries |  |  |  |  | Not Started
3.3 | Scoring & Coverage Tracking | 2 | [6 empty] | Not Started
3.3.1 | Running tally vs. evaluation weighting scheme | 3 | TN-EXT-05 | e.g. 70% Technical / 30% Financial |  |  |  |  | Not Started
3.3.2 | 100% coverage verification | 3 | TN-EXT-05 | Confirms extracted marks reconcile to full tender weighting |  |  |  |  | Not Started
4 | Evidence Matching Engine (Stage 3) | 1 | [6 empty] | Not Started
4.1 | Evidence Search & Scoring | 2 | [6 empty] | Not Started
4.1.1 | Query pre-indexed evidence database | 3 | TN-MTC-01 | Triggered for every requirement row needing supporting evidence |  |  |  |  | Not Started
4.1.2 | Hybrid semantic + metadata search | 3 | TN-MTC-02 | Dense vector similarity combined with sector/service line/client/keyword filters |  |  |  |  | Not Started
4.1.3 | Confidence scoring & thresholds | 3 | TN-MTC-03 | Auto-match >=0.85, Suggested 0.50-0.84, Missing Document <0.50 |  |  |  |  | Not Started
4.2 | Match Attachment & Review | 2 | [6 empty] | Not Started
4.2.1 | Attach matched file path(s) to requirement row | 3 | TN-MTC-04 | [5 empty] | Not Started
4.2.2 | Review UI: accept/reject/reassign matches | 3 | TN-MTC-05 | Sales manager review before final output generation |  |  |  |  | Not Started
5 | Output Assembly & Folder Creation (Stage 4) | 1 | [6 empty] | Not Started
5.1 | Excel Tracker Generation | 2 | [6 empty] | Not Started
5.1.1 | Main sheet generation | 3 | TN-OUT-01 | Page No., Section, Clause Ref, Description, Mandatory Flag, Evaluation Impact, Marks, Evidence Required, Matched File Path, Remarks |  |  |  |  | Not Started
5.1.2 | Summary sheet | 3 | TN-OUT-01 | Requirement counts and total marks breakdown by section/evaluation type |  |  |  |  | Not Started
5.1.3 | Instructions sheet | 3 | TN-OUT-01 | Notes on report usage and missing document flags |  |  |  |  | Not Started
5.2 | Folder & Archive Assembly | 2 | [6 empty] | Not Started
5.2.1 | Root directory creation | 3 | TN-OUT-02 | {TenderName}_{Date} naming convention |  |  |  |  | Not Started
5.2.2 | Populate root directory | 3 | TN-OUT-03 | Original tender + Excel tracker + Required Documents subfolder |  |  |  |  | Not Started
5.2.3 | ZIP packaging for download | 3 | TN-OUT-04 | [5 empty] | Not Started
5.3 | Summary Report Generation | 2 | [6 empty] | Not Started
5.3.1 | Optional .docx/.pdf summary report generator | 3 | TN-OUT-05 | [5 empty] | Not Started
6 | Evidence Library Management Subsystem | 1 | [6 empty] | Not Started
6.1 | Document Indexing & Vectorization Pipeline | 2 | [6 empty] | Not Started
6.1.1 | Multi-category indexing | 3 | LIB-IDX-01 | Case Studies (~40-50), Methodology Docs (~6-7), Company Documents (~15-20) |  |  |  |  | Not Started
6.1.2 | Case study parsing + image extraction | 3 | LIB-IDX-02 | Client/Sector/Scope/Challenge/Solution/Results sections; images stored on disk, linked via metadata path |  |  |  |  | Not Started
6.1.3 | Methodology parsing by phase/section | 3 | LIB-IDX-03 | [5 empty] | Not Started
6.1.4 | Company document single-purpose indexing | 3 | LIB-IDX-04 | Certificates, registrations, tax filings |  |  |  |  | Not Started
6.1.5 | Text chunking + embeddings | 3 | LIB-IDX-05 | ~800 tokens / 100-token overlap, stored in PostgreSQL pgvector |  |  |  |  | Not Started
6.1.6 | Metadata attribute extraction | 3 | LIB-IDX-06 | Document Type, Client, Sector, Service Line, Geography, Keywords |  |  |  |  | Not Started
6.1.7 | Incremental indexing | 3 | LIB-IDX-07 | New asset processed without re-indexing existing library |  |  |  |  | Not Started
6.2 | Library Frontend & Training Interface | 2 | [6 empty] | Not Started
6.2.1 | Dedicated category tabs | 3 | LIB-UI-01 | Case Studies / Methodology Documents / Company Documents |  |  |  |  | Not Started
6.2.2 | Drag-and-drop upload control | 3 | LIB-UI-02 | PDF, DOCX, PPTX, image formats |  |  |  |  | Not Started
6.2.3 | Metadata input fields + auto-tagging fallback | 3 | LIB-UI-03 | Client, Sector, Service Line |  |  |  |  | Not Started
6.2.4 | "Train / Memorize" action | 3 | LIB-UI-04 | Triggers background indexing pipeline for queued files |  |  |  |  | Not Started
6.2.5 | Real-time training status feedback | 3 | LIB-UI-05 | WebSocket: Parsing -> Tagging -> Generating Embeddings -> Indexing Complete |  |  |  |  | Not Started
6.2.6 | Pre-training duplicate checks | 3 | LIB-UI-06 | File hash + semantic similarity warning |  |  |  |  | Not Started
6.2.7 | Hot-reload availability for Stage 3 matching | 3 | LIB-UI-07 | No server restart required |  |  |  |  | Not Started
7 | Progress Tracking & Real-Time Feedback | 1 | [6 empty] | Not Started
7.1 | Live Progress Streaming | 2 | [6 empty] | Not Started
7.1.1 | WebSocket streaming during tender processing | 3 | TRK-01 | [5 empty] | Not Started
7.1.2 | Progress payload | 3 | TRK-02 | Current step, total steps, step label, % completion, extracted requirement counts |  |  |  |  | Not Started
7.1.3 | Explicit pipeline stage tracking | 3 | TRK-03 | Parse -> Chunk -> Extract -> Merge -> Match -> Report -> Assemble Folder -> Review |  |  |  |  | Not Started
7.1.4 | Resume/reconnect handling | 3 | TRK-04 | Navigate away or close tab, return later to view progress/results |  |  |  |  | Not Started
8 | Frontend Shell & Shared UI | 1 | [6 empty] | Not Started
8.1 | Core Application Shell | 2 | [6 empty] | Not Started
8.1.1 | Root layout + navigation | 3 |  | Role-aware nav for Admin / Manager / User |  |  |  |  | Not Started
8.1.2 | Login page + auth hook / API client | 3 | AUTH-02 | [5 empty] | Not Started
8.1.3 | Role-based route guarding | 3 | AUTH-04 | Hides admin-only screens from non-admins |  |  |  |  | Not Started
8.1.4 | WebSocket connection manager | 3 | TRK-01 | Shared client used by tender progress and library training feedback |  |  |  |  | Not Started
8.2 | Tender Workflow UI | 2 | [6 empty] | Not Started
8.2.1 | Tender upload zone | 3 | TN-ING-01 | [5 empty] | Not Started
8.2.2 | Live progress tracker component | 3 | TRK-02 | WebSocket-driven step/percentage display |  |  |  |  | Not Started
8.2.3 | Requirements table view | 3 | TN-EXT-02 | [5 empty] | Not Started
8.2.4 | Evidence review panel + finalize action | 3 | TN-MTC-05 | Accept/reject/reassign matches, trigger Stage 4 output |  |  |  |  | Not Started
9 | Integration & Testing | 1 | [6 empty] | Not Started
9.1 | Backend Testing | 2 | [6 empty] | Not Started
9.1.1 | Unit tests: auth & RBAC | 3 | AUTH-* | [5 empty] | Not Started
9.1.2 | Unit tests: chunking & extraction | 3 | TN-ING-*, TN-EXT-* | [5 empty] | Not Started
9.1.3 | Unit tests: evidence matching & scoring | 3 | TN-MTC-* | [5 empty] | Not Started
9.1.4 | Integration tests: end-to-end tender pipeline | 3 | TRK-03 | All 8 pipeline stages, Parse through Review |  |  |  |  | Not Started
9.2 | Frontend Testing | 2 | [6 empty] | Not Started
9.2.1 | Component testing | 3 |  | Upload zone, requirements table, review panel |  |  |  |  | Not Started
9.2.2 | WebSocket progress UI testing | 3 | TRK-01..04 | [5 empty] | Not Started
9.3 | System Testing | 2 | [6 empty] | Not Started
9.3.1 | Load/performance testing | 3 | TN-ING-01 | 500+ page tenders, large evidence library corpus |  |  |  |  | Not Started
9.3.2 | Security testing | 3 | AUTH-* | JWT handling, RBAC enforcement, password encryption |  |  |  |  | Not Started
9.3.3 | User Acceptance Testing (UAT) | 3 |  | With engineering, PM, QA, and sales stakeholders |  |  |  |  | Not Started
10 | Deployment & Documentation | 1 | [6 empty] | Not Started
10.1 | Production deployment (Docker Compose) | 3 |  | Company network or cloud VPS |  |  |  |  | Not Started
10.2 | Database migration to production | 3 |  | Alembic upgrade |  |  |  |  | Not Started
10.3 | User documentation / manual | 3 |  | Admin/Sales Lead, User/Sales Analyst roles |  |  |  |  | Not Started
10.4 | Technical / handover documentation | 3 |  | Architecture, API reference, runbook |  |  |  |  | Not Started
10.5 | Final demo & presentation | 3 |  | To PM, QA, and sales department stakeholders |  |  |  |  | Not Started

## Instructions
How to Use This WBS Spreadsheet
STRUCTURE
This WBS is organized as: Level 1 = Major deliverable/module, Level 2 = Sub-deliverable/phase, Level 3 = Work package (the actual assignable task).
Every Level 3 row is small enough that one person (or pair) can own it and it can be marked done/not done unambiguously.
COLUMNS TO FILL IN (highlighted in yellow on the WBS sheet, Level 3 rows only)
- Owner: the team member responsible for that work package.
- Start Date / End Date: your planned schedule for that item. Once filled in, you can generate a Gantt chart from these two columns.
- Est. Effort (days): your estimate of person-days to complete the work package.
- Status: use the dropdown (Not Started / In Progress / Blocked / Done).
- Dependencies: WBS Code(s) of items that must finish first.
- Notes: risks, blockers, or clarifications specific to that task.
LINKED REQUIREMENT ID(S)
Cross-references back to the Software Requirements Specification (e.g., AUTH-01, TN-ING-04, TN-EXT-05, TN-MTC-03, TN-OUT-02, LIB-IDX-05, LIB-UI-04, TRK-02).
This lets you trace every SRS requirement to at least one WBS work package, and back again, which is what satisfies the 100% Rule (all scope is covered, nothing extra is being built).
HOW TO ADAPT THIS
- If your team is smaller than the module split suggests, merge Level 2 branches under one owner rather than deleting work packages.
- If a work package feels too big to estimate confidently, split it further (add a Level 4, e.g., 6.1.2.1) rather than guessing.
- Keep the WBS Code stable once you start scheduling/tracking against it -- treat renumbering as a breaking change to your plan.
TURNING THIS INTO A SCHEDULE
Once Owner/Start/End are filled in for all Level 3 rows, this table maps directly into a Gantt chart (e.g., paste into MS Project, or plot Start/End per row in Excel/PowerPoint).